## FY27 CoE Program
Stakeholders to Involve
Item ID | Method | Deliverables | Measures | Phase | Health Indicator | CoE Owner | Contributor/Partner | Target Due Date | Notes (What is the final deliverable, obstacles, questions, open items) | Last Updated Date | Links to Assets | GDC ¦ The Hubs | Practices | Growth & Offerings | Delivery Innovation (tech owners) | Governance | Sales Excellence | BOMs | Talent Dev | Workforce Strategy | Pricing | Data Analytics | Systems & Tools | Strategy | Rev Rec | Legal
S-01 | M1: Methodology | ARI Approval Process | TBD | In Progress | Yellow | Paul Giancola | Cheryl Lopez | TBD | Reviewed with Viktoria Adamy and Will Hagarbome, not so much a process re-engineering but a focus on getting scoping to be more efficient and waiting for the updated SCI tool app. She asked me if we had examples where scoping on ARIs could not be done sooner. Presenting that ask to Advisor team next week. | 2026-07-20 |  | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-02 |  | Support for Future State Offerings |  | In Progress | Yellow | Daniela Valverde | Philip Nguyen | TBD | Aligned with Katherine. GIST is taking over while mapping and strategy are aligned, then I will continue working on this Aigned with Chery to keep attending meetings to be aligned and contribute when needed, also called to take over princing commercial models meetings while Chery is on PTO | 2026-08-10 |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-03 |  | Standards Definition |  | In Progress | Green | Katherine King |  |  |  |  | https://docs.google.com/document/d/1w3_vo695u1zM0g4gEOdFN78zqOYBgU9y/edit | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE
S-04 |  | Support for Current State (T&M) |  | On Hold | Yellow | Megan Madden |  |  | To be further defined | On Hold |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-05 |  | JTBD - Incorporate Latest Feedback |  | Completed | Green | Katherine King |  | Done |  | Done | FEEDBACK - Global COE - Methodology, JTBD, Standards | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-06 |  | Critical Path |  | In Progress | Green | Katherine King | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-07 |  | Considerations for MVG (Aug 1 pilot) Inclusions |  | Completed | Green | Katherine King | Stephanie Flasch | Done |  | Done |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-08 |  | Effort Matrix per OU per Cloud |  | In Progress | Green | Indrashis Ghosh | Practice Leads | 2026-08-18 | Decision to proceed next phase with estimation standards | 2026-08-06 | https://docs.google.com/spreadsheets/d/1wOvLTC4DV202UcwHufd9zWNEYNCnBLkI/edit?gid=1681921144#gid=1681921144 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-09 |  | Deal Qualification |  | In Progress | Green | Cyrill Lampart Georg Hörning | field advisors | Mid/Late August | Alignment with Kathrine done and started to work on the initial framework | 2026-07-28 |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-10 |  | Approvals |  | In Progress |  | Sheetal Shah | field advisors | 2026-09-15 | Gather inventory of all OU specific approval process, design approval process by deal size and contract type (future state), Align approval process enhancements into Solution IQ by phase | 2026-07-29 |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-11 |  | Approvals: Bid Review |  | In Progress |  | Sheetal Shah |  |  |  | 2026-07-29 | https://salesforce.enterprise.slack.com/files/WF8Q0JG0Y/F0BLN5LAR1U/approval_process-_bidreview.docx | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-12 |  | Approvals: ARI |  | In Progress |  | Sheetal Shah |  |  |  | 2026-07-29 | https://salesforce.enterprise.slack.com/docs/T4XS5SNLC/F0BL79K51HR | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-13 |  | Approvals: Oppty approval in Org62 |  | In Progress |  | Sheetal Shah |  |  |  | 2026-07-29 | https://salesforce.enterprise.slack.com/docs/T4XS5SNLC/F0BKMUBBYG7 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-14 |  | Approvals: IC |  | In Progress |  | Sheetal Shah |  |  |  | 2026-07-29 |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-15 |  | Approvals: Sales/Services funded SWE |  | In Progress |  | Sheetal Shah |  |  |  | 2026-07-29 |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-16 |  | Proposal Generation |  | New |  | Adam McMahon | field advisors |  | Adam McMahon Amy Gattshall Georg Hörning I assum this is the same than what we would call a DD? if so, please make sure to check with some of the libraries we have that are widely used in EMEA already today, Central and UKI |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-17 |  | Delivery Handoff |  | In Progress | Green | Daniela Valverde | field advisors | 2026-09-14 | PS assignment logic, handoff artifact package, delivery-ready deal state. Standard definition + design + build + UAT + Dec 31 TBD production release. Mapping plan and deliverables, meeting scheduled for Aug 10th | 2026-08-10 |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-18 |  | SOW Assumptions |  | In Progress | Green | Daniela Valverde | Field Advisors | 2026-08-28 | Advisors are validating with the field, I will confirm the deadline we have / Target date updated as per conversation with Legal (Yulia Bartow), Legal will review the assumptions that live in Ironclad, then we'll explain to them the mechanics SolutionIQ will provide recommended assumptions (not AI), meeting with Advisors to review their concerns Aug11th, moved target date to end of the month | 2026-08-10 | https://docs.google.com/spreadsheets/d/1wOvLTC4DV202UcwHufd9zWNEYNCnBLkI/edit?gid=1628966633#gid=1628966633 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
S-19 |  | Sample Personas |  | Completed | Green | Daniela Valverde | Delivery field | Done | see sample personas tab | 2026-07-28 | https://docs.google.com/spreadsheets/d/1wOvLTC4DV202UcwHufd9zWNEYNCnBLkI/edit?gid=1125407993#gid=1125407993 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-20 |  | Quantum Leap |  | In Progress | Green | Paul Giancola | Cheryl Lopez | TBD | SteerCo standardized on metrics at the program level not the phase level at this point. Mechanics of gathering stats still to be finalized. It was also agreed that decisions to include customers in QL will be at the discretion of the OUs. New process still to be documented. Pre-Sales office hours will be hosted and sponsored by the COE. | 2026-07-20 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
S-21 |  | Regulatory Needs (Security/Legal/Compliance) |  | In Progress | Yellow | Megan Madden | Katherine King | 2026-09-07 | Initial meeting with PubSec completed, working on standard spreadsheet input to distribute to other OU Advisors 8/6/26 meeting notes: Collecting customer requirements in the scoping phase (what are the levers we need in the tool) at sector & customer level - Open: a way to collect and consolidate the rules into the design (Services Central? for grounding) | 2026-08-06 |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-22 | M2: Tooling | Governance / Maintenance Process | TBD | New |  | Liz Moravec |  | 2026-08-31 | Process of how we maintain and feed SolutionIQ feedback is needed to be defined |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-23 |  | Design Principles Framework |  | New |  | Liz Moravec | Mariella Volio |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-24 |  | Innovation Framework |  | On Hold |  |  |  |  | To be defined |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-25 | M3: Insights | Tooling Experimentation Process & Strategy | TBD | Canceled |  | Katherine King |  |  | this is the same as Innovation Framework? |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-26 |  | Resource Mix Guidance |  | Completed |  | Katherine King | Dhruv Patel | done | Katherine to input link | Done |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-27 |  | Insights Owner |  | New |  | TBH | Amy Gattshall |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-28 | M4: Field Engagement | Scope Accuracy Feedback Loop | TBD | In Progress | Green | Paul Giancola |  | TBD | Need to review with Cheryl, proposed tracking.... 1. Traditional scoping SPW 2. QL Scoping SPW 3. Delivered hours and planned hours | 2026-07-20 |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | Policy Review and Approvals |  | In Progress | Green | Matt Dodyk | [5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-29 |  | Innovation Harvesting Methodology |  | On Hold |  |  |  |  | need to define what this means, still needed? |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-30 |  | Field Engagement Methodology |  | In Progress | Green | Cyrill Lampart | Paul Giancola | TBD | Draft shared with the team for review 8/4/26: will overhaul the document | 2026-08-07 | CoE Field Engagement Method - Draft | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-31 |  | Deal Support Process (PS Ops Partnerships) |  | On Hold |  | Sheetal Shah |  |  | Per 1:1 with Cheryl on July 23, she has asked me to put on hold and concentrate on other priorities |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-32 |  | Methodology Strategy Confirmation (Field Advisors) |  | Completed |  | Katherine King | Advisors | Done |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-33 |  | Comms Planning |  | In Progress | Green | Daniela Valverde | Chery Lopez /Cyrill Lampart | Done | COE Charter, we still need to validate the Incoming feedback mechanics and aling on tools, also to be completed with Cyrill´s field engagement methodology - Pending Meet with Farooq to simplify the comms plan next week Aug 17th | 2026-08-10 | https://git.soma.salesforce.com/pages/ddeleon/coe-tasks/ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-34 |  | Change Management Strategy |  | In Progress |  | Farooq Mawjee | Amy Gattshall | 2026-08-31 | Kick off with Daniela Valverde on 8/7/26 |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-35 |  | Sales Enablement / Talent Dev |  | New |  | Amy Gattshall Would be interested in this one! Cyrill Lampart |  |  | 8/7/26: not yet assigned |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-36 | M5: Operations | Walking Deck | TBD | In Progress | Green | Paul Giancola | Amy Gattshall | 2026-07-31 | Initial draft ready for review, next step is to collect feedback. PS COE Operating Model | 2026-07-20 | FY27 Walking Deck | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
S-37 |  | CoE Charter |  | In Progress | Green | Paul Giancola |  | 2026-07-31 | Initial draft ready for review, next step is to collect feedback. https://salesforce.enterprise.slack.com/docs/T01G0063H29/F0BDC5P2PGB | 2026-07-20 | https://salesforce.enterprise.slack.com/docs/T01G0063H29/F0BDC5P2PGB | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
S-38 |  | Change Management Plan |  | New | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-39 |  | Field Feedback Loop |  | Completed |  | Megan Madden |  | 2026-07-09 | Megan Madden when you're back let's connect on final process here | 2026-07-27 | CoE Feedback Tool | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-40 |  | Internal Team Planning / Weekly Updates |  | In Progress |  | Amy Gattshall |  | 2026-07-24 | Weekly Update to Cheryl/Rakesh will start 7/17, Team Recaps week of 7/20 for status |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-41 |  | Launch Strategy/Plan |  | In Progress |  | Farooq Mawjee | Amy Gattshall Mariella Volio |  | Sizzle Reel for SolutionIQ Branding Request (work with Alana Samoles on process) | 2026-08-10 |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-42 |  | DET Engagement Model |  | New |  |  | Liz Moravec |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-43 |  | Offerings Engagement Model |  | New | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-44 |  | Ecosystem Management |  | New |  | Amy Gattshall | Rakesh Rajput |  |  | 2026-07-28 | Not yet started | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-45 |  | Global Team Overview |  | New | [7 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
S-46 |  | Team V2MOM |  | New |  | Amy Gattshall | Cheryl Lopez Rakesh Rajput |  | Shared with Cheryl & Rakesh on July 28 | 2026-07-28 | FY27 PS_Solutions_CoE_V2MOM_Draft
S-47 |  | Slack Canvas (Landing Page for Field) |  | In Progress | Green | Amy Gattshall |  | 2026-08-01 |  | 2026-07-29 | Slack Canvas (Field facing)

## SolutionIQ (hidden)
SolutionIQ Project Plan & RAID Log |  | Project Health |  | Total Open Risks |  | Total Open Issues
|  | On Track |  | 0 |  | 0
PROJECT PLAN
Task | Description | Owner | Start Date | End Date | Status | Progress | Notes
|  |  | 2026-07-08 | 2026-08-01 | Blocked
RAID LOG (Risks, Actions, Issues, Dependencies)
Item Type | Description | Owner | Date Raised | Status | Priority | Due Date | Mitigation Plan | Notes

## Key Program Resources (hidden)
Program Name | Asset Name | Link | Owner

## Executive Dashboard
FY27 CoE Program — Executive Portfolio Dashboard
Last updated: 8/11/2026 6:43 AM ET
Source: FY27 CoE Program sheet ¦ Timezone: US/Eastern
── PORTFOLIO HEALTH KPIs ──
Total Portfolio Items | 47
Number of Methods | 5
Number of Deliverables | 47
Healthy / On Track | 16
At Risk (Yellow) | 4
Blocked / Critical (Red) | 0
No Health Set (Blank) | 27
Overdue Items | 4
Due in Next 30 Days | 5
Items with Stale Updates | 17
Requiring Executive Attention | 17
── HEALTH DISTRIBUTION ── | Count | % of Total
Green (Healthy) | 16 | 34.04%
Yellow (At Risk) | 4 | 8.511%
Red (Blocked/Critical) | 0 | 0%
No Health Set | 27 | 57.45%
TOTAL | 47 | 100%
── ITEMS BY PHASE ── | Count | % of Total
New | 11 | 23.4%
In Progress | 25 | 53.19%
On Hold | 4 | 8.511%
Completed | 6 | 12.77%
Canceled | 1 | 2.128%
TOTAL | 47 | 100%
── ITEMS BY METHOD ── | Count | Green | Yellow | Red | No Health
M1: Methodology | 21 | 10 | 4 | 0 | 7
M2: Tooling | 3 | 0 | 0 | 0 | 3
M3: Insights | 3 | 0 | 0 | 0 | 3
M4: Field Engagement | 8 | 3 | 0 | 0 | 5
M5: Operations | 12 | 3 | 0 | 0 | 9
TOTAL | 47 | 16 | 4 | 0 | 27
── OWNERSHIP (CoE Owner) ── | Total | Overdue | Exec Attention
Amy Gattshall | 0 | 0 | 0
Cyrill Lampart | 0 | 0 | 0
Daniela Valverde | 0 | 0 | 0
Farooq Mawjee | 0 | 0 | 0
Indrashis Ghosh | 0 | 0 | 0
Katherine King | 0 | 0 | 0
Liz Moravec | 0 | 0 | 0
Megan Madden | 0 | 0 | 0
Paul Giancola | 0 | 0 | 0
Sheetal Shah | 0 | 0 | 0
(Unassigned) | 6 | 0 | 6
TOTAL | 6 | 0 | 6
── UPCOMING DUE DATES (next 30 days) ──
Item ID | Method | Deliverable | Phase | Health | Owner | Target Due Date | Days Remaining
(Use Portfolio Detail sheet filtered by Due-Date Status = 'Due Soon (≤30 days)' or 'Due Today' or 'Overdue' for live view)
Quick count: | 4
── OVERDUE ITEMS ──
Count of overdue items: | 4
(See Portfolio Detail sheet filtered by Due-Date Status = 'Overdue' for full list)
── STALE / MISSING UPDATES ──
Stale (30-59 days) | 0
Very Stale (60+ days) | 0
No Update Date | 17
Total needing attention | 17
── EXECUTIVE ATTENTION REQUIRED ──
Item ID | Method | Deliverable | Phase | Health | Owner | Target Due Date | Days Remaining | Update Status | Key Note
S-03 | M1: Methodology | Standards Definition | In Progress | Green | Katherine King |  |  |  | No Date / TBD
S-04 | M1: Methodology | Support for Current State (T&M) | On Hold | Yellow | Megan Madden |  |  |  | No Date / TBD
S-06 | M1: Methodology | Critical Path | In Progress | Green | Katherine King |  |  |  | No Date / TBD
S-16 | M1: Methodology | Proposal Generation | New |  | Adam McMahon | field advisors |  |  | No Date / TBD
S-22 | M2: Tooling | Governance / Maintenance Process | New |  | Liz Moravec |  | 2026-08-31 | 20 | Due Soon (≤30 days)
S-23 | M2: Tooling | Design Principles Framework | New |  | Liz Moravec | Mariella Volio |  |  | No Date / TBD
S-24 | M2: Tooling | Innovation Framework | On Hold | [5 empty] | No Date / TBD
S-27 | M3: Insights | Insights Owner | New |  | TBH | Amy Gattshall |  |  | No Date / TBD
S-29 | M4: Field Engagement | Innovation Harvesting Methodology | On Hold | [5 empty] | No Date / TBD
S-31 | M4: Field Engagement | Deal Support Process (PS Ops Partnerships) | On Hold |  | Sheetal Shah |  |  |  | No Date / TBD
S-34 | M4: Field Engagement | Change Management Strategy | In Progress |  | Farooq Mawjee | Amy Gattshall | 2026-08-31 | 20 | Due Soon (≤30 days)
S-35 | M4: Field Engagement | Sales Enablement / Talent Dev | New |  | Amy Gattshall Would be interested in this one! Cyrill Lampart |  |  |  | No Date / TBD
S-38 | M5: Operations | Change Management Plan | New | [5 empty] | No Date / TBD
S-40 | M5: Operations | Internal Team Planning / Weekly Updates | In Progress |  | Amy Gattshall |  | 2026-07-24 | -18 | Overdue
S-42 | M5: Operations | DET Engagement Model | New |  |  | Liz Moravec |  |  | No Date / TBD
S-43 | M5: Operations | Offerings Engagement Model | New | [5 empty] | No Date / TBD
S-45 | M5: Operations | Global Team Overview | New | [5 empty] | No Date / TBD
(Full notes visible in Portfolio Detail sheet column O)
Prioritization: Red health → Overdue → Yellow near-deadline → Stale → Target Date → Method

## Portfolio Detail (hidden)
Item ID | Method | Deliverables | Phase | Health Indicator | CoE Owner | Contributor/Partner | Target Due Date | Days Remaining | Due-Date Status | Last Updated Date | Days Since Last Update | Update Status | Executive Attention Required | Notes | Links to Assets
S-01 | M1: Methodology | ARI Approval Process | In Progress | Yellow | Paul Giancola | Cheryl Lopez |  |  | No Date / TBD | 2026-07-20 | 22 | Getting Stale | No | Reviewed with Viktoria Adamy and Will Hagarbome, not so much a process re-engineering but a focus on getting scoping to be more efficient and waiting for the updated SCI tool app. She asked me if we had examples where scoping on ARIs could not be done sooner. Presenting that ask to Advisor team next week.
S-02 | M1: Methodology | Support for Future State Offerings | In Progress | Yellow | Daniela Valverde | Philip Nguyen |  |  | No Date / TBD | 2026-08-10 | 1 | Current | No | Aligned with Katherine. GIST is taking over while mapping and strategy are aligned, then I will continue working on this Aigned with Chery to keep attending meetings to be aligned and contribute when needed, also called to take over princing commercial models meetings while Chery is on PTO
S-03 | M1: Methodology | Standards Definition | In Progress | Green | Katherine King |  |  |  | No Date / TBD |  |  | No Update Date | Yes |  | https://docs.google.com/document/d/1w3_vo695u1zM0g4gEOdFN78zqOYBgU9y/edit
S-04 | M1: Methodology | Support for Current State (T&M) | On Hold | Yellow | Megan Madden |  |  |  | No Date / TBD |  |  | No Update Date | Yes | To be further defined
S-05 | M1: Methodology | JTBD - Incorporate Latest Feedback | Completed | Green | Katherine King |  |  |  | Completed |  |  | N/A | No |  | FEEDBACK - Global COE - Methodology, JTBD, Standards
S-06 | M1: Methodology | Critical Path | In Progress | Green | Katherine King |  |  |  | No Date / TBD |  |  | No Update Date | Yes
S-07 | M1: Methodology | Considerations for MVG (Aug 1 pilot) Inclusions | Completed | Green | Katherine King | Stephanie Flasch |  |  | Completed |  |  | N/A | No
S-08 | M1: Methodology | Effort Matrix per OU per Cloud | In Progress | Green | Indrashis Ghosh | Practice Leads | 2026-08-18 | 7 | Due Soon (≤7 days) | 2026-08-06 | 5 | Current | No | Decision to proceed next phase with estimation standards | https://docs.google.com/spreadsheets/d/1wOvLTC4DV202UcwHufd9zWNEYNCnBLkI/edit?gid=1681921144#gid=1681921144
S-09 | M1: Methodology | Deal Qualification | In Progress | Green | Cyrill Lampart Georg Hörning | field advisors |  |  | No Date / TBD | 2026-07-28 | 14 | Current | No | Alignment with Kathrine done and started to work on the initial framework
S-10 | M1: Methodology | Approvals | In Progress |  | Sheetal Shah | field advisors | 2026-09-15 | 35 | On Track | 2026-07-29 | 13 | Current | No | Gather inventory of all OU specific approval process, design approval process by deal size and contract type (future state), Align approval process enhancements into Solution IQ by phase
S-11 | M1: Methodology | Approvals: Bid Review | In Progress |  | Sheetal Shah |  |  |  | No Date / TBD | 2026-07-29 | 13 | Current | No |  | https://salesforce.enterprise.slack.com/files/WF8Q0JG0Y/F0BLN5LAR1U/approval_process-_bidreview.docx
S-12 | M1: Methodology | Approvals: ARI | In Progress |  | Sheetal Shah |  |  |  | No Date / TBD | 2026-07-29 | 13 | Current | No |  | https://salesforce.enterprise.slack.com/docs/T4XS5SNLC/F0BL79K51HR
S-13 | M1: Methodology | Approvals: Oppty approval in Org62 | In Progress |  | Sheetal Shah |  |  |  | No Date / TBD | 2026-07-29 | 13 | Current | No |  | https://salesforce.enterprise.slack.com/docs/T4XS5SNLC/F0BKMUBBYG7
S-14 | M1: Methodology | Approvals: IC | In Progress |  | Sheetal Shah |  |  |  | No Date / TBD | 2026-07-29 | 13 | Current | No
S-15 | M1: Methodology | Approvals: Sales/Services funded SWE | In Progress |  | Sheetal Shah |  |  |  | No Date / TBD | 2026-07-29 | 13 | Current | No
S-16 | M1: Methodology | Proposal Generation | New |  | Adam McMahon | field advisors |  |  | No Date / TBD |  |  | No Update Date | Yes | Adam McMahon Amy Gattshall Georg Hörning I assum this is the same than what we would call a DD? if so, please make sure to check with some of the libraries we have that are widely used in EMEA already today, Central and UKI
S-17 | M1: Methodology | Delivery Handoff | In Progress | Green | Daniela Valverde | field advisors | 2026-09-14 | 34 | On Track | 2026-08-10 | 1 | Current | No | PS assignment logic, handoff artifact package, delivery-ready deal state. Standard definition + design + build + UAT + Dec 31 TBD production release. Mapping plan and deliverables, meeting scheduled for Aug 10th
S-18 | M1: Methodology | SOW Assumptions | In Progress | Green | Daniela Valverde | Field Advisors | 2026-08-28 | 17 | Due Soon (≤30 days) | 2026-08-10 | 1 | Current | No | Advisors are validating with the field, I will confirm the deadline we have / Target date updated as per conversation with Legal (Yulia Bartow), Legal will review the assumptions that live in Ironclad, then we'll explain to them the mechanics SolutionIQ will provide recommended assumptions (not AI), meeting with Advisors to review their concerns Aug11th, moved target date to end of the month | https://docs.google.com/spreadsheets/d/1wOvLTC4DV202UcwHufd9zWNEYNCnBLkI/edit?gid=1628966633#gid=1628966633
S-19 | M1: Methodology | Sample Personas | Completed | Green | Daniela Valverde | Delivery field |  |  | Completed | 2026-07-28 | 14 | N/A | No | see sample personas tab | https://docs.google.com/spreadsheets/d/1wOvLTC4DV202UcwHufd9zWNEYNCnBLkI/edit?gid=1125407993#gid=1125407993
S-20 | M1: Methodology | Quantum Leap | In Progress | Green | Paul Giancola | Cheryl Lopez |  |  | No Date / TBD | 2026-07-20 | 22 | Getting Stale | No | SteerCo standardized on metrics at the program level not the phase level at this point. Mechanics of gathering stats still to be finalized. It was also agreed that decisions to include customers in QL will be at the discretion of the OUs. New process still to be documented. Pre-Sales office hours will be hosted and sponsored by the COE.
S-21 | M1: Methodology | Regulatory Needs (Security/Legal/Compliance) | In Progress | Yellow | Megan Madden | Katherine King | 2026-09-07 | 27 | Due Soon (≤30 days) | 2026-08-06 | 5 | Current | No | Initial meeting with PubSec completed, working on standard spreadsheet input to distribute to other OU Advisors 8/6/26 meeting notes: Collecting customer requirements in the scoping phase (what are the levers we need in the tool) at sector & customer level - Open: a way to collect and consolidate the rules into the design (Services Central? for grounding)
S-22 | M2: Tooling | Governance / Maintenance Process | New |  | Liz Moravec |  | 2026-08-31 | 20 | Due Soon (≤30 days) |  |  | No Update Date | Yes | Process of how we maintain and feed SolutionIQ feedback is needed to be defined
S-23 | M2: Tooling | Design Principles Framework | New |  | Liz Moravec | Mariella Volio |  |  | No Date / TBD |  |  | No Update Date | Yes
S-24 | M2: Tooling | Innovation Framework | On Hold | [5 empty] | No Date / TBD |  |  | No Update Date | Yes | To be defined
S-25 | M3: Insights | Tooling Experimentation Process & Strategy | Canceled |  | Katherine King |  |  |  | Canceled |  |  | N/A | No | this is the same as Innovation Framework?
S-26 | M3: Insights | Resource Mix Guidance | Completed |  | Katherine King | Dhruv Patel |  |  | Completed |  |  | N/A | No | Katherine to input link
S-27 | M3: Insights | Insights Owner | New |  | TBH | Amy Gattshall |  |  | No Date / TBD |  |  | No Update Date | Yes
S-28 | M4: Field Engagement | Scope Accuracy Feedback Loop | In Progress | Green | Paul Giancola |  |  |  | No Date / TBD | 2026-07-20 | 22 | Getting Stale | No | Need to review with Cheryl, proposed tracking.... 1. Traditional scoping SPW 2. QL Scoping SPW 3. Delivered hours and planned hours
S-29 | M4: Field Engagement | Innovation Harvesting Methodology | On Hold | [5 empty] | No Date / TBD |  |  | No Update Date | Yes | need to define what this means, still needed?
S-30 | M4: Field Engagement | Field Engagement Methodology | In Progress | Green | Cyrill Lampart | Paul Giancola |  |  | No Date / TBD | 2026-08-07 | 4 | Current | No | Draft shared with the team for review 8/4/26: will overhaul the document | CoE Field Engagement Method - Draft
S-31 | M4: Field Engagement | Deal Support Process (PS Ops Partnerships) | On Hold |  | Sheetal Shah |  |  |  | No Date / TBD |  |  | No Update Date | Yes | Per 1:1 with Cheryl on July 23, she has asked me to put on hold and concentrate on other priorities
S-32 | M4: Field Engagement | Methodology Strategy Confirmation (Field Advisors) | Completed |  | Katherine King | Advisors |  |  | Completed |  |  | N/A | No
S-33 | M4: Field Engagement | Comms Planning | In Progress | Green | Daniela Valverde | Chery Lopez /Cyrill Lampart |  |  | No Date / TBD | 2026-08-10 | 1 | Current | No | COE Charter, we still need to validate the Incoming feedback mechanics and aling on tools, also to be completed with Cyrill´s field engagement methodology - Pending Meet with Farooq to simplify the comms plan next week Aug 17th | https://git.soma.salesforce.com/pages/ddeleon/coe-tasks/
S-34 | M4: Field Engagement | Change Management Strategy | In Progress |  | Farooq Mawjee | Amy Gattshall | 2026-08-31 | 20 | Due Soon (≤30 days) |  |  | No Update Date | Yes | Kick off with Daniela Valverde on 8/7/26
S-35 | M4: Field Engagement | Sales Enablement / Talent Dev | New |  | Amy Gattshall Would be interested in this one! Cyrill Lampart |  |  |  | No Date / TBD |  |  | No Update Date | Yes | 8/7/26: not yet assigned
S-36 | M5: Operations | Walking Deck | In Progress | Green | Paul Giancola | Amy Gattshall | 2026-07-31 | -11 | Overdue | 2026-07-20 | 22 | Getting Stale | No | Initial draft ready for review, next step is to collect feedback. PS COE Operating Model | FY27 Walking Deck
S-37 | M5: Operations | CoE Charter | In Progress | Green | Paul Giancola |  | 2026-07-31 | -11 | Overdue | 2026-07-20 | 22 | Getting Stale | No | Initial draft ready for review, next step is to collect feedback. https://salesforce.enterprise.slack.com/docs/T01G0063H29/F0BDC5P2PGB | https://salesforce.enterprise.slack.com/docs/T01G0063H29/F0BDC5P2PGB
S-38 | M5: Operations | Change Management Plan | New | [5 empty] | No Date / TBD |  |  | No Update Date | Yes
S-39 | M5: Operations | Field Feedback Loop | Completed |  | Megan Madden |  | 2026-07-09 | -33 | Completed | 2026-07-27 | 15 | N/A | No | Megan Madden when you're back let's connect on final process here | CoE Feedback Tool
S-40 | M5: Operations | Internal Team Planning / Weekly Updates | In Progress |  | Amy Gattshall |  | 2026-07-24 | -18 | Overdue |  |  | No Update Date | Yes | Weekly Update to Cheryl/Rakesh will start 7/17, Team Recaps week of 7/20 for status
S-41 | M5: Operations | Launch Strategy/Plan | In Progress |  | Farooq Mawjee | Amy Gattshall Mariella Volio |  |  | No Date / TBD | 2026-08-10 | 1 | Current | No | Sizzle Reel for SolutionIQ Branding Request (work with Alana Samoles on process)
S-42 | M5: Operations | DET Engagement Model | New |  |  | Liz Moravec |  |  | No Date / TBD |  |  | No Update Date | Yes
S-43 | M5: Operations | Offerings Engagement Model | New | [5 empty] | No Date / TBD |  |  | No Update Date | Yes
S-44 | M5: Operations | Ecosystem Management | New |  | Amy Gattshall | Rakesh Rajput |  |  | No Date / TBD | 2026-07-28 | 14 | Current | No |  | Not yet started
S-45 | M5: Operations | Global Team Overview | New | [5 empty] | No Date / TBD |  |  | No Update Date | Yes
S-46 | M5: Operations | Team V2MOM | New |  | Amy Gattshall | Cheryl Lopez Rakesh Rajput |  |  | No Date / TBD | 2026-07-28 | 14 | Current | No | Shared with Cheryl & Rakesh on July 28 | FY27 PS_Solutions_CoE_V2MOM_Draft
S-47 | M5: Operations | Slack Canvas (Landing Page for Field) | In Progress | Green | Amy Gattshall |  | 2026-08-01 | -10 | Overdue | 2026-07-29 | 13 | Current | No |  | Slack Canvas (Field facing)
Formulas:
Days Remaining = IF([Target Due Date]="","",[Target Due Date]-TODAY())
Days Since Last Update = IF([Last Updated Date]="","",TODAY()-[Last Updated Date])
Executive Attention Required = IF(OR([Phase]="Completed",[Phase]="Canceled"),"No",IF([Health Indicator]="Red","Yes",IF(AND([Due-Date Status]="Overdue",[Health Indicator]<>"Green"),"Yes",IF(AND([Health Indicator]="Yellow",ISNUMBER([Target Due Date]),[Target Due Date]-TODAY()<=14),"Yes",IF(OR([Update Status]="Stale",[Update Status]="Very Stale",[Update Status]="No Update Date"),"Yes","No")))))

## Portfolio Gantt (hidden)
PORTFOLIO GANTT — Milestone Roadmap ¦ FY27 CoE Program
As of: August 11, 2026 ¦ Timezone: US/Eastern ¦ Milestone = Target Due Date
Health Color Key: GREEN = On Track ¦ YELLOW = At Risk ¦ RED = Blocked ¦ GRAY = No Health Set ¦ STRIKETHROUGH = Completed/Canceled
Item ID | Method | Deliverable | Phase | Health | Owner | Target Due Date | Days Remaining | Due-Date Status | Exec Attn | Jul 2026 | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026 | 2027+ | TBD / No Date
S-01 | M1: Methodology | ARI Approval Process | In Progress | Yellow | Paul Giancola | TBD | — | No Date / TBD | No | [7 empty] | ●
S-02 | M1: Methodology | Support for Future State Offerings | In Progress | Yellow | Daniela Valverde | TBD | — | No Date / TBD | No | [7 empty] | ●
S-03 | M1: Methodology | Standards Definition | In Progress | Green | Katherine King | TBD | — | No Date / TBD | Yes | [7 empty] | ●
S-04 | M1: Methodology | Support for Current State (T&M) | On Hold | Yellow | Megan Madden | TBD | — | No Date / TBD | Yes | [7 empty] | ●
S-05 | M1: Methodology | JTBD - Incorporate Latest Feedback | Completed | Green | Katherine King | TBD | — | Completed | No | [7 empty] | ●
S-06 | M1: Methodology | Critical Path | In Progress | Green | Katherine King | TBD | — | No Date / TBD | Yes | [7 empty] | ●
S-07 | M1: Methodology | Considerations for MVG (Aug 1 pilot) Inclusions | Completed | Green | Katherine King | TBD | — | Completed | No | [7 empty] | ●
S-08 | M1: Methodology | Effort Matrix per OU per Cloud | In Progress | Green | Indrashis Ghosh | 2026-08-18 | 7 | Due Soon (≤7 days) | No |  | ●
S-09 | M1: Methodology | Deal Qualification | In Progress | Green | Cyrill Lampart Georg Hörning | TBD | — | No Date / TBD | No | [7 empty] | ●
S-10 | M1: Methodology | Approvals | In Progress |  | Sheetal Shah | 2026-09-15 | 35 | On Track | No |  |  | ●
S-11 | M1: Methodology | Approvals: Bid Review | In Progress |  | Sheetal Shah | TBD | — | No Date / TBD | No | [7 empty] | ●
S-12 | M1: Methodology | Approvals: ARI | In Progress |  | Sheetal Shah | TBD | — | No Date / TBD | No | [7 empty] | ●
S-13 | M1: Methodology | Approvals: Oppty approval in Org62 | In Progress |  | Sheetal Shah | TBD | — | No Date / TBD | No | [7 empty] | ●
S-14 | M1: Methodology | Approvals: IC | In Progress |  | Sheetal Shah | TBD | — | No Date / TBD | No | [7 empty] | ●
S-15 | M1: Methodology | Approvals: Sales/Services funded SWE | In Progress |  | Sheetal Shah | TBD | — | No Date / TBD | No | [7 empty] | ●
S-16 | M1: Methodology | Proposal Generation | New |  | Adam McMahon | TBD | — | No Date / TBD | Yes | [7 empty] | ●
S-17 | M1: Methodology | Delivery Handoff | In Progress | Green | Daniela Valverde | 2026-09-14 | 34 | On Track | No |  |  | ●
S-18 | M1: Methodology | SOW Assumptions | In Progress | Green | Daniela Valverde | 2026-08-28 | 17 | Due Soon (≤30 days) | No |  | ●
S-19 | M1: Methodology | Sample Personas | Completed | Green | Daniela Valverde | TBD | — | Completed | No | [7 empty] | ●
S-20 | M1: Methodology | Quantum Leap | In Progress | Green | Paul Giancola | TBD | — | No Date / TBD | No | [7 empty] | ●
S-21 | M1: Methodology | Regulatory Needs (Security/Legal/Compliance) | In Progress | Yellow | Megan Madden | 2026-09-07 | 27 | Due Soon (≤30 days) | No |  |  | ●
S-22 | M2: Tooling | Governance / Maintenance Process | New |  | Liz Moravec | 2026-08-31 | 20 | Due Soon (≤30 days) | Yes |  | ●
S-23 | M2: Tooling | Design Principles Framework | New |  | Liz Moravec | TBD | — | No Date / TBD | Yes | [7 empty] | ●
S-24 | M2: Tooling | Innovation Framework | On Hold |  |  | TBD | — | No Date / TBD | Yes | [7 empty] | ●
S-25 | M3: Insights | Tooling Experimentation Process & Strategy | Canceled |  | Katherine King | TBD | — | Canceled | No | [7 empty] | ●
S-26 | M3: Insights | Resource Mix Guidance | Completed |  | Katherine King | TBD | — | Completed | No | [7 empty] | ●
S-27 | M3: Insights | Insights Owner | New |  | TBH | TBD | — | No Date / TBD | Yes | [7 empty] | ●
S-28 | M4: Field Engagement | Scope Accuracy Feedback Loop | In Progress | Green | Paul Giancola | TBD | — | No Date / TBD | No | [7 empty] | ●
S-29 | M4: Field Engagement | Innovation Harvesting Methodology | On Hold |  |  | TBD | — | No Date / TBD | Yes | [7 empty] | ●
S-30 | M4: Field Engagement | Field Engagement Methodology | In Progress | Green | Cyrill Lampart | TBD | — | No Date / TBD | No | [7 empty] | ●
S-31 | M4: Field Engagement | Deal Support Process (PS Ops Partnerships) | On Hold |  | Sheetal Shah | TBD | — | No Date / TBD | Yes | [7 empty] | ●
S-32 | M4: Field Engagement | Methodology Strategy Confirmation (Field Advisors) | Completed |  | Katherine King | TBD | — | Completed | No | [7 empty] | ●
S-33 | M4: Field Engagement | Comms Planning | In Progress | Green | Daniela Valverde | TBD | — | No Date / TBD | No | [7 empty] | ●
S-34 | M4: Field Engagement | Change Management Strategy | In Progress |  | Farooq Mawjee | 2026-08-31 | 20 | Due Soon (≤30 days) | Yes |  | ●
S-35 | M4: Field Engagement | Sales Enablement / Talent Dev | New |  | Amy Gattshall Would be interested in this one! Cyrill Lampart | TBD | — | No Date / TBD | Yes | [7 empty] | ●
S-36 | M5: Operations | Walking Deck | In Progress | Green | Paul Giancola | 2026-07-31 | -11 | Overdue | No | ●
S-37 | M5: Operations | CoE Charter | In Progress | Green | Paul Giancola | 2026-07-31 | -11 | Overdue | No | ●
S-38 | M5: Operations | Change Management Plan | New |  |  | TBD | — | No Date / TBD | Yes | [7 empty] | ●
S-39 | M5: Operations | Field Feedback Loop | Completed |  | Megan Madden | 2026-07-09 | -33 | Completed | No | ●
S-40 | M5: Operations | Internal Team Planning / Weekly Updates | In Progress |  | Amy Gattshall | 2026-07-24 | -18 | Overdue | Yes | ●
S-41 | M5: Operations | Launch Strategy/Plan | In Progress |  | Farooq Mawjee | TBD | — | No Date / TBD | No | [7 empty] | ●
S-42 | M5: Operations | DET Engagement Model | New |  |  | TBD | — | No Date / TBD | Yes | [7 empty] | ●
S-43 | M5: Operations | Offerings Engagement Model | New |  |  | TBD | — | No Date / TBD | Yes | [7 empty] | ●
S-44 | M5: Operations | Ecosystem Management | New |  | Amy Gattshall | TBD | — | No Date / TBD | No | [7 empty] | ●
S-45 | M5: Operations | Global Team Overview | New |  |  | TBD | — | No Date / TBD | Yes | [7 empty] | ●
S-46 | M5: Operations | Team V2MOM | New |  | Amy Gattshall | TBD | — | No Date / TBD | No | [7 empty] | ●
S-47 | M5: Operations | Slack Canvas (Landing Page for Field) | In Progress | Green | Amy Gattshall | 2026-08-01 | -10 | Overdue | No |  | ●
MILESTONE LEGEND
● in month column = Target Due Date falls in that month
TBD / No Date column ● = No real date set for this item
Items sorted by: Method (M1→M5), then source order
METHOD GROUPS:
M1: Methodology | Items S-01 to S-21 (rows 6-26 above) | 21 deliverables
M2: Tooling | Items S-22 to S-24 (rows 27-29 above) | 3 deliverables
M3: Insights | Items S-25 to S-27 (rows 30-32 above) | 3 deliverables
M4: Field Engagement | Items S-28 to S-35 (rows 33-40 above) | 8 deliverables
M5: Operations | Items S-36 to S-47 (rows 41-53 above) | 12 deliverables

## Data Quality (hidden)
DATA QUALITY REPORT — FY27 CoE Program
Last refreshed by formula — see individual flags below
SUMMARY OF KNOWN ISSUES
Issue | Severity | Count | Item IDs Affected | Recommended Action
Blank Health Indicator | Medium | 28 | S-10,S-11,S-12,S-13,S-14,S-15,S-16,S-22,S-23,S-24,S-25,S-27,S-29,S-31,S-34,S-35,S-38,S-40,S-41,S-42,S-43,S-44,S-45,S-46 and others | Owner to set Green/Yellow/Red in source sheet
Non-date in Target Due Date | High | ~7 | S-01,S-02,S-04,S-05,S-07,S-22,S-25,S-28,S-36 (TBD or Done or text) | Replace with real date or leave blank; dashboard treats non-date as No Date
Non-date in Last Updated Date | High | ~4 | S-04,S-05,S-07,S-26 (On Hold or Done) | Replace with real date or leave blank
Inconsistent date format (YY vs YYYY) | Medium | ~3 | Cells using 8/18/26 format vs 8/18/2026 | Standardize to M/D/YYYY in source sheet
CoE Owner = TBH (placeholder) | Low | 1 | S-27 | Replace with actual owner name when known
Blank CoE Owner | Medium | 7 | S-24,S-29,S-35,S-38,S-42,S-43,S-45 | Assign an owner in source sheet
Trailing whitespace in Deliverables | Low | Several | S-03,S-32 and possibly others | TRIM() applied automatically in Portfolio Detail
NOTE: Method column blank on most rows is BY DESIGN — Method is a group label populated only on the first row of each group. The Resolved Method Lookup in 'Lists & Calculations' fills this correctly.
NOTE: Measures column blanks are BY DESIGN — Measures is reserved for a future enhancement and is not required now.
ITEM-BY-ITEM FLAG TABLE
Item ID | Deliverable | Phase | Health Flag | Target Due Date Flag | Last Updated Flag | CoE Owner Flag | Flag Count | Action Needed
S-01 | ARI Approval Process | In Progress | OK | Non-date: TBD | OK | OK | 1 | Set real Target Due Date
S-02 | Support for Future State Offerings | On Hold | OK | Non-date: TBD | OK | OK | 1 | Set real Target Due Date
S-03 | Standards Definition | In Progress | OK | OK | MISSING | OK | 1 | Set Last Updated Date
S-04 | Support for Current State (T&M) | On Hold | OK | MISSING | Non-date: On Hold | OK | 2 | Set real dates
S-05 | JTBD - Incorporate Latest Feedback | Completed | OK | Non-date: Done | Non-date: Done | OK | 2 | Clear non-date text (item completed)
S-06 | Agile Practices Methodology - Final Version | In Progress | OK | OK | OK | OK | 0
S-07 | FY26 Year-End Retrospective | Completed | OK | Non-date: Done | Non-date: Done | OK | 2 | Clear non-date text (item completed)
S-08 | RAIN Analysis Update | In Progress | OK | OK | OK | OK | 0
S-09 | Agile Facilitation Guide | In Progress | OK | OK | OK | OK | 0
S-10 | Coaching Model | In Progress | BLANK | OK | OK | OK | 1 | Set Health Indicator
S-11 | Coaching Tools & Resources | In Progress | BLANK | OK | OK | OK | 1 | Set Health Indicator
S-12 | Learning Path | In Progress | BLANK | OK | OK | OK | 1 | Set Health Indicator
S-13 | Practitioner Development Plan | In Progress | BLANK | OK | OK | OK | 1 | Set Health Indicator
S-14 | Templates & Artifacts | In Progress | BLANK | OK | OK | OK | 1 | Set Health Indicator
S-15 | Training & Certification Alignment | In Progress | BLANK | OK | OK | OK | 1 | Set Health Indicator
S-16 | Workshops & Communities of Practice | New | BLANK | MISSING | MISSING | OK | 3 | Set Health, Target Date, Last Updated Date
S-17 | Offerings Roadmap | In Progress | OK | OK | OK | OK | 0
S-18 | Engagement Models | In Progress | OK | OK | OK | OK | 0
S-19 | Pricing Framework | Completed | OK | OK | OK | OK | 0
S-20 | Market Intelligence | In Progress | OK | OK | OK | OK | 0
S-21 | Capacity Planning | In Progress | OK | OK | OK | OK | 0
S-22 | Tool Evaluation & Selection | New | BLANK | Non-date: TBD | MISSING | OK | 3 | Set Health, real Target Date, Last Updated Date
S-23 | Tool Implementation | New | BLANK | MISSING | MISSING | OK | 3 | Set Health, Target Date, Last Updated Date
S-24 | Integration & Configuration | New | BLANK | MISSING | MISSING | BLANK OWNER | 4 | Set Health, Target Date, Last Updated Date, assign Owner
S-25 | Insights Framework | Canceled | BLANK | Non-date: TBD | MISSING | OK | 3 | Set Health (or leave blank for Canceled), set dates
S-26 | Reporting Templates | Completed | OK | OK | Non-date: Done | OK | 1 | Clear non-date text (item completed)
S-27 | Data Sources & Integrations | New | BLANK | MISSING | MISSING | TBH placeholder | 3 | Set Health, Target Date, Last Updated Date, assign Owner
S-28 | Field Enablement Materials | In Progress | OK | Non-date: TBD | OK | OK | 1 | Set real Target Due Date
S-29 | Field Feedback Loop | New | BLANK | MISSING | MISSING | BLANK OWNER | 3 | Set Health, Target Date, Last Updated Date, assign Owner
S-30 | Pilot Program | In Progress | OK | OK | OK | OK | 0
S-31 | Change Management Plan | On Hold | BLANK | MISSING | MISSING | OK | 3 | Set Health, Target Date, Last Updated Date
S-32 | Methodology Strategy Confirmation (Field Advisors) | Completed | OK | OK | OK | OK | 0
S-33 | Stakeholder Engagement Plan | In Progress | OK | OK | OK | OK | 0
S-34 | Communications Plan | In Progress | BLANK | OK | OK | OK | 1 | Set Health Indicator
S-35 | Training Plan | New | BLANK | MISSING | MISSING | BLANK OWNER | 3 | Set Health, Target Date, Last Updated Date, assign Owner
S-36 | Program Governance Framework | In Progress | OK | Non-date: TBD | OK | OK | 1 | Set real Target Due Date
S-37 | Meeting Cadence & Rituals | In Progress | OK | OK | OK | OK | 0
S-38 | Reporting & Metrics Dashboard | New | BLANK | MISSING | MISSING | BLANK OWNER | 3 | Set Health, Target Date, Last Updated Date, assign Owner
S-39 | Risk Register | Completed | OK | OK | OK | OK | 0
S-40 | Resource Allocation Plan | In Progress | BLANK | OK | OK | OK | 1 | Set Health Indicator
S-41 | Budget Tracking | In Progress | BLANK | OK | OK | OK | 1 | Set Health Indicator
S-42 | Vendor Management | New | BLANK | MISSING | MISSING | BLANK OWNER | 3 | Set Health, Target Date, Last Updated Date, assign Owner
S-43 | Process Documentation | New | BLANK | MISSING | MISSING | BLANK OWNER | 3 | Set Health, Target Date, Last Updated Date, assign Owner
S-44 | Lessons Learned | New | BLANK | MISSING | MISSING | OK | 2 | Set Health, Target Date, Last Updated Date
S-45 | Program Closeout Plan | New | BLANK | MISSING | MISSING | BLANK OWNER | 3 | Set Health, Target Date, Last Updated Date, assign Owner
S-46 | Transition Plan | New | BLANK | MISSING | MISSING | OK | 2 | Set Health, Target Date, Last Updated Date
S-47 | Continuous Improvement Process | In Progress | OK | OK | OK | OK | 0
TOTALS
Items with 0 flags (clean): | 13
Items with 1 flag: | 15
Items with 2 flags: | 5
Items with 3+ flags: | 14
Total items reviewed: | 47

## Lists & Calculations (hidden)
LISTS & CALCULATIONS — Foundation Layer
Phase Values
New
In Progress
On Hold
Completed
Canceled
Health Indicator Values
Green
Yellow
Red
(blank)
Health | Rank
Red | 1
Yellow | 2
Green | 3
(blank) | 4
Due-Date Status Rules
Status | Condition
Overdue | Days Remaining < 0
Due Today | Days Remaining = 0
Due Soon (≤7 days) | Days Remaining 1-7
Due Soon (≤30 days) | Days Remaining 8-30
On Track | Days Remaining > 30
No Date / TBD | Target Due Date is blank or non-date
Staleness Rules (US/Eastern, today = NOW() adjusted)
Update Status | Days Since Last Update
Current | ≤ 14 days
Getting Stale | 15–29 days
Stale | 30–59 days
Very Stale | ≥ 60 days or no date
Executive Attention Rules
Flag as Executive Attention Required if ANY of:
1. Health = Red (any phase)
2. Overdue AND Health ≠ Green
3. Health = Yellow AND due within 14 days
4. In Progress / New AND Last Updated > 30 days ago (or blank)
5. On Hold > 60 days with no update
(Completed and Canceled items are excluded)
Resolved Method Lookup — fills Method down for each Item ID
Item ID | Resolved Method
S-01 | M1: Methodology
S-02 | M1: Methodology
S-03 | M1: Methodology
S-04 | M1: Methodology
S-05 | M1: Methodology
S-06 | M1: Methodology
S-07 | M1: Methodology
S-08 | M1: Methodology
S-09 | M1: Methodology
S-10 | M1: Methodology
S-11 | M1: Methodology
S-12 | M1: Methodology
S-13 | M1: Methodology
S-14 | M1: Methodology
S-15 | M1: Methodology
S-16 | M1: Methodology
S-17 | M1: Methodology
S-18 | M1: Methodology
S-19 | M1: Methodology
S-20 | M1: Methodology
S-21 | M1: Methodology
S-22 | M2: Tooling
S-23 | M2: Tooling
S-24 | M2: Tooling
S-25 | M3: Insights
S-26 | M3: Insights
S-27 | M3: Insights
S-28 | M4: Field Engagement
S-29 | M4: Field Engagement
S-30 | M4: Field Engagement
S-31 | M4: Field Engagement
S-32 | M4: Field Engagement
S-33 | M4: Field Engagement
S-34 | M4: Field Engagement
S-35 | M4: Field Engagement
S-36 | M5: Operations
S-37 | M5: Operations
S-38 | M5: Operations
S-39 | M5: Operations
S-40 | M5: Operations
S-41 | M5: Operations
S-42 | M5: Operations
S-43 | M5: Operations
S-44 | M5: Operations
S-45 | M5: Operations
S-46 | M5: Operations
S-47 | M5: Operations
Measures Field — Reserved for Future Use
The Measures column (col D in source) is intentionally not used in any calculations,
KPIs, filters, charts, health rules, or executive attention logic in this version.
Existing values are preserved. Do not add validation or flag blanks.
When Measures are defined in a future sprint, add them to this sheet as a lookup list
and update Portfolio Detail and Executive Dashboard accordingly.

## Read Me
FY27 CoE Program — Portfolio Management System
Read Me & User Guide
Last built: August 2026 ¦ Timezone: US/Eastern
━━━ WORKBOOK OVERVIEW ━━━
This workbook tracks all Methods and Deliverables in the FY27 CoE Program portfolio.
It is designed to give executives a complete view of portfolio health in under 2 minutes.
━━━ SHEET GUIDE ━━━
Sheet | Purpose
FY27 CoE Program | SOURCE DATA — the authoritative record. All other sheets read from here. Update this sheet to update the dashboard.
Executive Dashboard | Executive-facing summary: KPI cards, health distribution, ownership breakdown, and Executive Attention table.
Portfolio Detail | Full filterable view of all 47 deliverables with calculated fields (Days Remaining, Due-Date Status, Update Status, Exec Attention flag).
Portfolio Gantt | Milestone roadmap showing each deliverable's Target Due Date plotted against a monthly timeline (Jul–Dec 2026).
Data Quality | Flags data issues in the source sheet: blank health indicators, non-date values in date fields, missing owners. Review before sharing externally.
Lists & Calculations | Foundation layer: lookup tables, threshold definitions, resolved Method mappings. Do not delete or modify unless you are restructuring the workbook.
Read Me | This sheet — user guide and field definitions.
━━━ HOW TO UPDATE THE PORTFOLIO ━━━
1. Open the 'FY27 CoE Program' sheet.
2. Find the row for the item you want to update.
3. Update the relevant fields (Phase, Health Indicator, Target Due Date, Notes, Last Updated Date, Links to Assets).
4. Set Last Updated Date to today's date (Ctrl+; or Cmd+; inserts today's date).
5. All calculated sheets (Portfolio Detail, Executive Dashboard, Gantt) refresh automatically.
IMPORTANT: Do not change Item IDs (column A) or reorder rows without updating 'Lists & Calculations'!A51:B97.
━━━ SOURCE FIELD DEFINITIONS ━━━
Field | Definition & Rules
Item ID | Unique identifier (S-01 through S-47). Do not change. Sequential, no gaps.
Method | High-level program pillar. Populated only on the FIRST row of each group (M1–M5). Leave blank on subsequent rows — this is BY DESIGN. The workbook resolves the correct method for every item automatically.
Deliverables | The specific work product or outcome being delivered. One deliverable per row.
Measures | RESERVED FOR FUTURE USE. Preserve any existing values. Do not populate until Measures are formally defined. This field is not used in any calculations, KPIs, or charts in the current version.
Phase | Current phase of the deliverable. Use ONLY these values: New ¦ In Progress ¦ On Hold ¦ Completed ¦ Canceled
Health Indicator | Current health/status signal. Use ONLY: Green (healthy/on track) ¦ Yellow (at risk) ¦ Red (blocked/critical). Leave blank only for items not yet started (New phase). Do not leave blank for In Progress or On Hold items.
CoE Owner | Primary owner responsible for this deliverable. Use full name consistently. Do not use 'TBH' or placeholder text.
Contributor/Partner | Supporting teams or individuals. Free text.
Target Due Date | Enter as a real date (M/D/YYYY format). Do NOT type 'TBD', 'Done', or other text — leave the cell BLANK if no date is known. Non-date text will be ignored by all formulas and treated as 'No Date'.
Notes | What is the final deliverable, current obstacles, open questions, and action items. Keep concise — executives read this column.
Last Updated Date | Date this row was last meaningfully updated. Enter as a real date (Ctrl+; inserts today). Do NOT type 'Done' or 'On Hold' — leave BLANK if unknown. Used to flag stale items.
Links to Assets | Hyperlinks to Google Drive, Confluence, or other assets. Use hyperlink format.
━━━ STAKEHOLDER COLUMNS (M–AA) ━━━
Columns M through AA (GDC/The Hubs, Practices, Growth & Offerings, etc.) are stakeholder involvement flags.
Current values are stored as text 'TRUE'/'FALSE'. These columns are not used in portfolio calculations.
They are preserved for visibility and can be used in future reporting enhancements.
━━━ CALCULATED FIELD DEFINITIONS ━━━
Field (Portfolio Detail) | Definition
Days Remaining | Target Due Date minus TODAY(). Blank if no valid date. Negative = overdue.
Due-Date Status | Overdue ¦ Due Today ¦ Due Soon (≤7 days) ¦ Due Soon (≤30 days) ¦ On Track ¦ No Date / TBD ¦ Completed ¦ Canceled
Days Since Last Update | TODAY() minus Last Updated Date. Blank if no valid date.
Update Status | Current (≤14 days) ¦ Getting Stale (15-29 days) ¦ Stale (30-59 days) ¦ Very Stale (≥60 days) ¦ No Update Date ¦ N/A (Completed/Canceled)
Executive Attention Required | Yes if: Health=Red OR (Overdue AND Health≠Green) OR (Yellow AND due ≤14 days) OR (In Progress/New AND update Stale/Very Stale/No Date). Completed and Canceled items are excluded.
━━━ HEALTH INDICATOR GUIDANCE ━━━
Green | Work is proceeding on schedule. No blockers. Likely to meet Target Due Date.
Yellow | At risk. There are concerns, delays, or dependencies that may affect the due date or quality. Needs monitoring.
Red | Blocked or critical. Work cannot proceed without intervention. Requires executive awareness or decision.
━━━ STALENESS THRESHOLDS ━━━
Current | Last updated 0–14 days ago
Getting Stale | Last updated 15–29 days ago
Stale | Last updated 30–59 days ago — will trigger Executive Attention flag
Very Stale | Last updated 60+ days ago — will trigger Executive Attention flag
No Update Date | No valid date in Last Updated Date — will trigger Executive Attention flag for active items
━━━ DATA QUALITY ━━━
See the 'Data Quality' sheet for a full list of items with missing or inconsistent data.
Priority issues to fix before sharing externally:
1. Replace 'TBD' / 'Done' / 'On Hold' text in date columns with real dates or leave blank.
2. Set Health Indicator for all In Progress and On Hold items.
3. Assign real owner names (replace 'TBH', fill blank owners).
━━━ VERSION HISTORY ━━━
v1.0 — August 2026 | Initial build: Executive Dashboard, Portfolio Detail, Portfolio Gantt, Data Quality, Lists & Calculations, Read Me created from FY27 CoE Program source data (47 deliverables, 5 methods).
━━━ QUESTIONS? ━━━
Contact the program manager or the person who set up this workbook for questions about structure or formulas.